## Project Management Steps
Project Plan Template
| Task Name | Status | Start Date | Due Date | Assigned To | Flagged | Description
| Get started with Project Management | Not Started |  |  |  | Flagged | At Project Central we divide our Project Management approach into two very simple phases - "Plan a Project" and then "Manage a Project". This template is designed to help you effectivley manage a project, covering all the areas required to make sure it's a success.
Phase 1 | Plan a Project | [5 empty] | At Project Central we think about planning a project in three simple steps (Select Project Environment, Initiate the Project, Plan the Project).
Step 1 | Select Project Environment
| Access Project Environment | [5 empty] | Select a project collaboration environment that is easy to access for your team.
| Verify Security | [5 empty] | Check that this environment is secure for your organization.
| Check Experience | [5 empty] | Ensure the user experience will entice people to want to work on the project.
Step 2 | Initiate the Project
| Create Project | [5 empty] | Create a new project, ideally using a relevant project template supplied by your organization.
| Initiate Project | [5 empty] | Initiate the new project by adding the essentials on a Dashboard (e.g. Name, Objectives, Start and End Dates, Team Members, Project Tags)
| Invite Team Members | [5 empty] | Invite Team Members to their new project.
| Set Permissions | [5 empty] | Make sure only the authorized people can access the new project.
Step 3 | Plan the Project
| Layout the Project Structure | [5 empty] | Layout the structure (e.g. Phases, Sections) of how the project objectives will be achieved.
| Add Tasks | [5 empty] | Add the tasks needed to deliver the project - i.e. the tasks you know about at this stage.
| Setup the Schedule | [5 empty] | Move the task dates until you get a schedule that you and the team are comfortable with.
| Upload Files | [5 empty] | Choose a place to store the project deliverables and any other files associated with the project - and add the initial set.
Phase 2 | Manage a Project | [5 empty] | At Project Central we also think about managing a project in three simple steps (Collaborate as a Project Team, Track and Adjust the Project, Close out the Project).
Step 1 | Collaborate as a Project Team
| Setup Task Notifications | [5 empty] | Ensure Team Members are notified when they are assigned new Tasks or have Tasks due soon.
| Update Tasks | [5 empty] | Update the Tasks with more details on how the Tasks are or will be delivered.
| Monitor Project Activity | [5 empty] | Check in and monitor what is happening on the project (e.g. deadline changes, team member movements, status changes, etc.)
| Work Tasks on Other Projects | [5 empty] | Periodically review the Tasks due on other projects - so no balls are dropped by accident.
Step 2 | Track and Adjust the Project
| Resolve Flagged Tasks | [5 empty] | Start the Project Tracking by reviewing any Tasks flagged as requiring attention.
| Review Project Structure and Tasks | [5 empty] | Review the Project Structure (i.e. Phases, Sections) to ensure that it is still fit for purpose.
| Update Task Status | [5 empty] | Give your Team a sense of how the task is progressing by marking it "in progress" or "complete"
| Update Project Schedule | [5 empty] | Adjust the start and finish dates as necessary.
| Update Project Dashboard | [5 empty] | Update the Project Dashboard with the latest project status and overall health indicator of the project.
Step 3 | Close out the Project
| Close Project | [5 empty] | Make the final updates to the Project Dashboard (e.g. project status, etc.) and close out the project.
| Save Project as Template | [5 empty] | If the project has progressed successfully, save it is as a template use for you and your team, building project management best practices as you go.
All text and design is copyright © Project Central 2021 ¦ All rights reserved ¦

## ... with Project Central
Project Plan Template
| Task Name | Project Central Commentary
Phase 1 | Plan a Project | At Project Central we think about planning a project in three simple steps (Select Project Environment, Initiate the Project, Plan the Project).
Step 1 | Select Project Environment
| Access Project Environment | Project Central is an online solution, and subscription is managed very simply by credit card (though you can start a free trial without a credit card)
| Check Security | Navigate to ProjectCentral.com and sign-in using your Microsoft 365 work account, same username and password as you do at work every day.
| Check Experience | Project Central is designed with a super easy and intuitive user experience - specifically designed for the Occasional Project Manager.
Step 2 | Initiate the Project
| Create Project | Start a new project with a blank project or get an even faster and more relevant start with one of our Templates.
| Initiate Project | Initiate a new project in Project Central by adding the essentials on a Dashboard (e.g. Name, Objectives, Start and End Dates, Team Members, Project Tags)
| Invite Team Members | Project Central will send project invites to those you added to the project.
| Set Permissions | Project Central can invite anyone to the project from your Company Directory - and - you can also declare a project as a Private Project - and set the project to be viewable only by the Team Members
Step 3 | Plan the Project
| Layout the Project Structure | In Project Central, you can layout the structure (e.g. Phases, Sections) of how the project objectives will be achieved.
| Add Tasks | In Project Central, you can add and edit tasks in a project, assign to individual or multiple team members and add start and due dates.
| Setup the Schedule | In Project Central, move the tasks on the Gantt Chart until you get a schedule that you and the team are comfortable with.
| Add Files | In Project Central all your project deliverables are in one secure place, as you connect from Project Central to an existing SharePoint Online site.
Phase 2 | Manage a Project | At Project Central we also think about managing a project in three simple steps (Collaborate as a Project Team, Track and Adjust the Project, Close out the Project).
Step 1 | Collaborate with Project Team
| Update Tasks | In Project Central, project members can add more details to a specific task and elaborate on how they intent to deliver on a task. Team members can easily provide a status update, flag a task, add comments with @mentions which notify project members. The team can also attach files already in the Project Library or upload new files.
| Monitor Activity | Project Central gives your team the transparency on who and what is and isn’t working using the various activity feeds. The transparency allows you to have very open, honest and productive team meetings.
| Setup Task Notifications | In Project Central there are optional notifications available, e.g. Inviting a Project Member, Task Assigned and Task due soon.
Step 2 | Track & Adjust the Project
| Resolve Flagged Tasks | In Project Central, you can flag tasks which are critical to you or other project members.
| Review Project Structure and Tasks | In Project Central, you can select, drag and reorder multiple tasks. Project Central allows you to update or add new sections.
| View and Focus on selected tasks | In Project Central, you can filter tasks and my filters are saved from my last access. You can also adapt and change filters easily.
| Update Task Status | In Project Central, boards is a very fast way to get a visual Kanban style update and also quick to update Tasks status.
| Update Project Schedule | In Project Central, you can easily check the Gantt to check timelines once a project is moving.
| Update Project Dashboard | In Project Central, you can update the Project Tracker with the latest project status and the overall health of any project.
Step 3 | Close out the Project | l
| Close Project | Your project is now complete. Make any final amendments including the project status.
| Save Project as Template | If the project has progressed successfully, save it is a template for future use for you and your team and build best practices as you go.
Phase 3 | Manage Across Projects | At Project Central when we "Plan" and "Manage" many projects, we can manage our flow across many projects.
Step 1 | Manage Across Tasks
| Manage my Tasks | In Project Central, My Tasks allows you to view all your open and closed tasks across all projects and manage your work this way.
Step 2 | Manage Across Projects
| View related Projects | In Project Central, you can use the Project Cards to get an overview and quick access to all projects. The project Card display includes Project name, status, start and end date.
| Search and Sort Projects | In Project Central, you can search and order your projects in the order you wish to see them.
| Filter Projects | In Project Central, save your project filters for the next time log in or you can also clear your filters and start fresh.
| Report on Projects | In Project Central, you can export your project list view via Excel or PDF.
Step 3 | Manage Across Programs
| Manage Accounts | In Project Central, you can setup different Accounts, each that may have many projects - if you wish to keep sets of projects very separate.
| Setup Notifications | In Project Central, you can setup Notifications for: Account Invite, Project Invite, Task Assign or Tasks Due Soon … across all projects
| Manage Templates | In Project Central within the Templates area you can create new templates, modify, rename or delete existing Templates
| Manage Users | In Project Central, you can remove a user from all projects - e.g. if the person moves on from the organization
| Manage Tags | In Project Central, you can rename, change color or delete tags from all projects if you so wish!
All text and design is copyright © Project Central 2021 ¦ All rights reserved ¦